## Sheet1
Bug ID | Type | Feature | Description | Priority | Status | Assigned To | Reported By | Date Reported | Date Resolved | Comments/Notes
Bug - 001 | Bug | User Profile | When user uploads a photo, placeholder image doesn't get replaced until the users refreshs. This should be fix as soon as the upload is complete. | High | Fixed | Himel | Mamun | 2023-11-04 | 22/09/23
Bug - 002 | Bug | Market Place | Market listing is not appearing in reverse order | Critical | Not started | Bonni | Mamun | 2023-11-06 | 22/09/24
Bug - 003 | Bug | Registration | Button is not working in search button page. | Medium | In progress | Himel | Mamun | 2023-11-04 | 22/09/25
Bug - 004 | Bug | Performance | Employee tracker is not working properly | Medium | Fixed | Fariya | Bonni | 2023-11-08 | 22/09/26
Bug - 005 | Regression | Page editior | Lines break lost in code section | High | Functions as Designed | Himel | Himel | 2023-03-07 | 22/09/27
Bug - 006 | Bug | User Profile | Setting options shows highlighted even when mouse is not hovered on it | Medium | Not started | Mamun | Fariya | 22/07/2023 | 22/09/28
Bug - 007 | Investigation | PIM | All modules is not working properly | High | Not started | Mamun | Mamun | 25/08/2023 | 22/09/29
Bug - 008 | Change | My Info | Logo is not getting visible, it should be fixed. | Medium | In progress | Himel | Mamun | 30/08/2023 | 22/09/30